## pmr
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | (MIPA BARMM) Procurement Monitoring Report as of DECEMBER /31/2022
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| Check Printer | [19 empty] | MIPA Office | No | Small Value | [12 empty] | Dec. 16, 2022 | Capital Outlay | 30000 |  |  | 28392.86
| Executive Chair | [19 empty] | MIPA Office | No | Small Value | [12 empty] | Jan. 3, 2023 | Capital Outlay | 36000 |  |  | 35970
| CCTV | [19 empty] | MIPA Office | No | Small Value | [13 empty] | Capital Outlay | 35000 |  |  | 0
| Smart TV | [19 empty] | MIPA Office | No | Small Value | [12 empty] | Nov. 29, 2022 | Capital Outlay | 45000 |  |  | 42589.29
| Refrigerator | [19 empty] | MIPA Office | No | Small Value | [12 empty] | Nov. 29, 2022 | Capital Outlay | 30000 |  |  | 28392.86
| Projector | [19 empty] | MIPA Office | No | Small Value | [12 empty] | Nov. 10, 2022 | Capital Outlay | 35000 |  |  | 30758.93
| Industrial Fan | [19 empty] | MIPA Office | No | Small Value |  | Oct. 11, 2022 | [10 empty] | Nov. 29, 2022 | Capital Outlay | 60000 |  |  | 56785.71
| Portable Sound System | [19 empty] | MIPA Office | No | Small Value |  | Oct. 11, 2022 | [10 empty] | Nov. 29, 2022 | Capital Outlay | 60000 |  |  | 56785.71
| Photocopier | [19 empty] | MIPA Office | No | Small Value |  | Oct. 11, 2022 | [10 empty] | Nov. 15, 2022 | Capital Outlay | 75000 |  |  | 62464.29
| Air Purifier | [19 empty] | MIPA Office | No | Small Value |  | Oct. 11, 2022 | [10 empty] | Nov. 29, 2022 | Capital Outlay | 120000 |  |  | 106000
| Executive Table | [19 empty] | MIPA Office | No | Small Value |  | Oct. 10, 2022 | [10 empty] | Dec. 15, 2022 | Capital Outlay | 75000 |  |  | 70982.14
| Desktop Computer (10 units) | [19 empty] | MIPA Office | No | Small Value |  | Oct. 14, 2022 | [10 empty] | Dec. 2, 2022 | Capital Outlay | 450000 |  |  | 449950
| Junior Executive Chair | [19 empty] | MIPA Office | No | Small Value |  | Oct. 10,2022 | [10 empty] | Nov. 29, 2022 | Capital Outlay | 190000 |  |  | 179442.86
| Junior Executive Table | [19 empty] | MIPA Office | No | Small Value |  | Oct. 10, 2022 | [10 empty] | Jan. 3, 2023 | Capital Outlay | 300000 |  |  | 283928.57
| Steel Cabinet w/ vault | [19 empty] | MIPA Office | No | Small Value |  | Oct. 11, 2022 | [10 empty] | Dec. 2, 2022 | Capital Outlay | 300000 |  |  | 283815
| Parabolic Tent | [19 empty] | Community Service Centers | No | Small Value |  | May 25, 2022 | [10 empty] | Aug. 22, 2022 | Capital Outlay | 60000 |  |  | 58800
| Motorcycle ( 2 units) | [19 empty] | MIPA Office | No | Small Value |  | July 27, 2022 | [9 empty] | Nov. 10, 2022 | Nov. 10, 2022 | Capital Outlay | 150000 |  |  | 126405
| Laptop (12 units) | [19 empty] | MIPA Office | No | Small Value |  | Dec 26, 2022 | [10 empty] | Mar. 22, 2023 | Capital Outlay | 780000 |  |  | 780000
| Desktop Computer (12 units) | [19 empty] | MIPA Office | No | Small Value |  | Dec 26, 2022 | [10 empty] | Mar. 22, 2023 | Capital Outlay | 660000 |  |  | 660000
| Janitorial Services | [19 empty] | MIPA Office | No | Small Value |  | Feb. 23, 2022 | Mar 21, 2022 | Apr 11, 2022 | Apr 11, 2022 | Apr 12, 2022 | [7 empty] | Regular Fund | 814320 |  |  | 721191.6
| Security Services | [19 empty] | MIPA Office | No | Small Value |  | Feb. 23, 2022 | Mar 21, 2022 | Apr 11, 2022 | Apr 11, 2022 | Apr 12, 2022 | [7 empty] | Regular Fund | 864000 |  |  | 850500
| Motor Vehicle (pick up truck) | [19 empty] | MIPA Office | No | Public Bidding | May 9, 2022 | May 16, 2022 | May 21, 2022 | June 6, 2022 | June 6, 2022 | June 6, 2022 | June 9, 2022 |  | Sept. 20, 2022 | Sept. 28, 222 | Sept 28, 2022 | Nov. 4, 2022 | Nov. 7, 2022 | Capital Outlay | 1910000 |  |  | 1899000 |  |  | 1 |  |  | 06/03/2022 | 06/04/2022 | 06/06/2022 | 11/4/2022
| Social Preparation & Survey of Ancestral Domain of IP | [19 empty] | Community | No | Public Bidding | Mar. 7, 2022 | Mar. 16, 2022 | Mar 28, 2022 | Apr 11, 2022 | Apr 11, 2022 | Apr 12, 2022 | Apr 18, 2022 |  | April 25, 2022 | May 23, 2022 | May 10, 2022 |  |  | Regular Fund | 6979500 |  |  | 6977000 |  |  | 3 | 03/23/2022 |  |  |  | 04/15/2022
Total Alloted Budget of Procurement Activities | [37 empty] | 14058820
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 13789154.82
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 269665.18
0N-GOING PROCUREMENT ACTIVITIES
0
0
0
0
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 0
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | Suharto Ashraf L. Ibay | [10 empty] | Felino V. Samar | [10 empty] | Melanio U. Ulama
[21 empty] | BAC Secretariat | [10 empty] | BAC Chairperson | [10 empty] | Head of the Procuring Entity

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement